## Tasks
IMS Project
Goal: |  | Provide a portal any business peoples can use for their office and organization.
Deadline: |  | 2016-04-25
Members: |  | Jang, So, Kim
Task ID | Task Title | Task Description | Points | Dependency | Deadline | Processor | Assignee | Progress Stat
IMS-1-001 | PHP- 페지구조화 | 페지의 Header/Footer/Sidebar를 정의 | 3 |  | 2016-03-07 | Jang Myong Jin | Min Byong Guk | Accepted
IMS-1-002 | PHP- SESSION 관리 | Session.php 를 정의하고 Login 되지 않았으면 login 페지로 보낸다. | 1 |  | 2016-03-08 | Jang Myong Jin | Min Byong Guk | Accepted
IMS-1-003 | PHP- 사용자페지로 로그인 | pages/login.php 에서 사용자ID, 암호에 의한 가입구현, 암호는 MD5 알고리듬에 의해 암호화되여 자료기지에 보관되기 때문에 자료기지의 password 마당과 사용자가 입력한 password 에 MD5를 취하여 비교해야 한다. 사용자가 로그인에 성공하면 사용자 첫페지로 이동해야 한다. | 3 | IMS-1-007 | 2016-03-12 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-004 | jQuery - 사용자등록유효성검사 | jquery_validation plugin 에 의해 다음의 마당들에 대한 유효성을 검사한다. (사용자ID, 암호길이, 암호재입력,사용자이름, 직위, 주소, 생년월일 ) - 꼭 입력해야 할 마당 | 3 |  | 2016-03-12 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-005 | API - 사용자등록 | 사용자를 자료기지에 등록(사용자이름,암호… ) 암호는 MD5에 의해 암호화되여 자료기지에 보관, 사용자 사진에 대한 FileUpload 기능을 실현, 사용자ID가 중복되는 경우를 반영해야 한다. | 5 | IMS-1-004 | 2016-03-12 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-006 | Ajax - 사용자등록 API 와 사용자등록 Form 을 결합 | 사용자등록 Form 에서 등록단추를 누르면 먼저 Validation을 진행하고 모든 입력값이 유효하면 ajax에 의해 사용자등록 API를 호출한다. | 5 | IMS-1-005, IMS-1-004 | 2016-03-12 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-007 | PHP-로그인시 admin 인가를 식별 | 자료기지의 role 마당에 의해 만일 가입하는 사용자가 admin role을 가지면 admin 의 index 페지로 이행 | 2 | IMS-1-003 | 2016-03-12 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-008 | PHP-새소식부분 구현(첫 페지) | page.php에서 DB의 news표에서 가장 최근의 자료 5개의 자료를 꺼내서 반영 | 2 |  | 2016-03-11 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-009 | PHP-사업포치부분 구현(첫 페지) | page.php에서 DB의 work assignment표에서 오늘의 사업포치 자료를 꺼내서 반영 | 2 |  | 2016-03-11 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-010 | API-의견함자료 전송 | 의견내용이 자료기지의 opinions표에 보관되여야 한다. | 1 |  | 2016-03-11 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-011 | Ajax-의견함부분 구현(첫 페지) | 의견함전송API와 의견함Form을 결합시킨다. 전송단추를 누를때 Ajax에 의해서 의견함전송 API가 호출되여야 한다. API가 성공하는 경우 관리자에게 의견이 성과적으로 보내졌다는 BootStrap Style의 Alert가 현시 | 3 |  | 2016-03-11 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-012 | PHP-과학기술내용 구현(첫 페지)-인기기사 목록 | 자료기지의 bullet_in_board에서 1달내의 가장 인기있는 기사 10건을 꺼내서 목록으로 현시(*인기수는 starts마당에 의해서 결정한다.) | 5 | IMS-1-013 | 2016-03-11 | Jang Myong Jin | Min Byong Guk | Assigned
IMS-1-013 | PHP-과학기술내용 구현(첫 페지)-인기기사 내용 | 목록에서 1개항목을 누르면 그에 대한기사내용이 현시되여야 한다.'목록보기' link를 누르면 목록이 다시 보여진다. | 1 | IMS-1-012 | 2016-03-11 | Jang Myong Jin | Min Byong Guk | Assigned
IMS-1-014 | API - 전자게시판 기사투고 | API에 의해 투고된 기사가 DB의 bullet_in_board Table에 보관 | 2 | IMS-1-015 | 2016-03-13 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-015 | Ajax - 전자게시판 기사투고 | 기사투고 API와 Form 을 결합시킨다. 투고단추를 누를때 기사투고 API를 호출하는 Ajax를 구현 | 2 | IMS-1-014 | 2016-03-13 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-016 | API - 기사목록 얻기 | 한달이내의 모든 기사들을 DB의 bullet_in_board에서 얻어온다. 이때 users Table을 련결시켜 기사투고자의 Photo_url을 얻어야 한다 련결조건(bulllet_in_board.poster_id=users.user_id) | 5 |  | 2016-03-13 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-017 | Ajax-기사목록 얻기 | API와 결합시켜 얻은 목록들을 전자게시판페지에 현시해준다. 이때 추가단추와 삭제단추를 현시해준다. | 14 |  | 2016-03-21 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-018 | PHP-기사삭제 | 현시되여 있는 기사를 삭제한다. | 15 |  | 2016-03-22 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-017 | jQuery - 사용자등록유효성검사 |  | 16 |  | 2016-03-23 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-018 | jQuery - 사용자등록유효성검사 |  | 17 |  | 2016-03-24 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-019 | jQuery - 사용자등록유효성검사 |  | 18 |  | 2016-03-25 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-020 | jQuery - 사용자등록유효성검사 |  | 19 |  | 2016-03-26 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-021 | jQuery - 사용자등록유효성검사 |  | 20 |  | 2016-03-27 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-022 | jQuery - 사용자등록유효성검사 |  | 21 |  | 2016-03-28 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-023 | jQuery - 사용자등록유효성검사 |  | 22 |  | 2016-03-29 | So Jong Hyon | Min Byong Guk | Assigned
IMS-1-024 | jQuery - 사용자등록유효성검사 |  | 23 |  | 2016-03-30 | So Jong Hyon | Min Byong Guk | Assigned

## APIs
Application Programming Interface (Restful API)
Base url: http://localhost/ims/
URL | Method | Request | Response | Description / Related Task
/apis/v1/index.php | POST | { "cmd": "front-registeruser", "username": "mbk", "password": "test", "realname": "Min Byong Gukr", "gender": "MALE", "birthday": "1988-11-5", "address": "PyongYang", "position": "Engineer", "phonenum": "191-277-0758", "photo": <info of photo> } | success case { "code": "200" } failed case { "code": "301", "msg": "duplicate user name" } | IMS-1-005
/apis/v1/index.php | POST | { "cmd": "front-registeruser", "subject": "나의 의견", "content": "홈페지의 속도를 개선해 주십시요." } | success case { "code": "200" } | IMS-1-010
/apis/v2/index.php | POST | { "cmd": "front-addbulletin", "parent_id":1, "bullet_title":"나의 기사", "bullet_content":"기사내용', "bullet_type":"B_NEW" } | success case { "code": "200" } | IMS-1-014
/apis/v3/index.php | POST
/apis/v4/index.php | POST

## Points
Total Points | 4 | 0 | 0
Date | Jang Myong Jin | Kim Il Guk | So Jong Hyon
2016-03-07 | 4 | 0 | 0 | 4
2016-03-08
2016-03-09
2016-03-10
2016-03-11
2016-03-12
2016-03-13
2016-03-14
2016-03-15
2016-03-16
2016-03-17
2016-03-18
2016-03-19
2016-03-20
2016-03-21
2016-03-22
2016-03-23
2016-03-24
2016-03-25
2016-03-26
2016-03-27
2016-03-28
2016-03-29
2016-03-30
2016-03-31
2016-04-01
2016-04-02
2016-04-03
2016-04-04
2016-04-05
2016-04-06
2016-04-07
2016-04-08
2016-04-09
2016-04-10
2016-04-11
2016-04-12
2016-04-13
2016-04-14
2016-04-15
2016-04-16
2016-04-17
2016-04-18
2016-04-19
2016-04-20
2016-04-21
2016-04-22
2016-04-23
2016-04-24
2016-04-25

## Tasks-old
IMS Project
Goal: |  | Provide a portal any business peoples can use for their office and organization.
Deadline: |  | 2016-04-25
Members: |  | Jang, So, Kim
Task ID | Task Title | Task Description | Points | Deadline | Processor | Assignee | Progress Stat
IMS-2-001 | Api- Approve User in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | So Jong Hyon | Min Byong Guk | Started
IMS-2-002 | Api-List Users in Admin | Make an api for retrieve all registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-07 | So Jong Hyon | Min Byong Guk | Finished
IMS-2-003 | Api- User detail in Admin | Make an api to get detail of a selected user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Delayed
IMS-2-004 | Api- List presents in Admin | Make an api for listing presented users in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-005 | Api- List resources in Admin | Make an api for listing information of resources in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-08 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-006 | Api- Add resource in Admin | Make an api for uploading files to Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-08 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-007 | Api- Edit resource in Admin | Make an api for editing information of resources in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-08 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-008 | Api- Remove resource in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-08 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-009 | Api- Approve resource in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-08 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-010 | Api- List bulletins in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-08 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-011 | Api- Add builletins in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-08 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-012 | Api- Edit bulletins in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-013 | Api- Remove bulletins in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-014 | Api- Approve bulletin in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-015 | Api- List worklog in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-016 | Api- Approve worklog in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-017 | Api- List news in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-018 | Api- Add news in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-019 | Api- Edit news in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-020 | Api- Remove news in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-021 | Api- List Projects in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-022 | Api- Add Project in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-023 | Api- Edit project in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-024 | Api- Remove project in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-025 | Api- List tasks in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-026 | Api- Add task in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-027 | Api- Edit task in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-028 | Api- Remove task in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-029 | Api- Assign task in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-030 | Api- Compose mail in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-031 | Api- List mails by type in Admin (Inbox/ draft / trash / sent) | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-07 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-032 | Api- Trash/Draft mail in Admin by updating status | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-033 | PHP-Login to Admin with admin account | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | So Jong Hyon | Min Byong Guk | Assigned
IMS-2-034 | Api- List work assignments in Admin | Make an api for listing work assignments in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-07 | Jang Myong Jin | Min Byong Guk | Finished
IMS-2-035 | Api- Add daily report in Admin | Make an api for adding daily report in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Jang Myong Jin | Min Byong Guk | Finished
IMS-2-036 | Api- Edit daily orgnized work in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-037 | Api- Remove daily orgnized work in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-038 | Api- Update profile in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-039 | Api- List advices in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-040 | Api- Remove advice in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-001 | PHP-structuring pages with including header/footer | Split pages with common header/footer and define snippets in includes sub directory. | 5 | 2016-03-07 | Jang Myong Jin | Min Byong Guk | Assigned
IMS-1-002 | jQuery- validate registration form in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-003 | Api- Register user in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-004 | Api- List my worklog in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-005 | Api- Add my worklog in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-006 | Api- Edit my worklog in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-007 | Api- Post advice in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-008 | Api-Comment on a bulletin in Front Bulletin Board | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-009 | Api- List bulletins in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-010 | Api- Detail all comments for a selected builletin in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-011 | Api- List all resources in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-08 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-012 | Api- Post a resource in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-09 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-013 | Api- Compose mail in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-10 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-014 | Api- List mails by type in Admin (Inbox/ draft / trash / sent) in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-11 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-015 | Api- Trash/Draft mail in Admin by updating status in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-12 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-016 | PHP- Login to IMS front portal with <username,pass> pairs | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 5 | 2016-03-13 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-017 | Ajax- Integration registration api with registering form | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 8 | 2016-03-14 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-018 | PHP- reflect news to first page | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-15 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-019 | PHP- reflect orgnized works to first page | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 2 | 2016-03-16 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-020 | Api- Update login status for logged in user in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-17 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-021 | Api- List all logged in users in Front Chat Room | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-18 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-022 | Api- Send a message to any online user | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-19 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-023 | Api- List all received messages in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-20 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-024 | Api- Get number of unread mails and list of them | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 3 | 2016-03-21 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-025 | Ajax- Integration post bulletin form with api in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-22 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-026 | Ajax- Integration comment bulletin form with API in front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-23 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-027 | Ajax- Integration post resource form with api in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-24 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-028 | Ajax- Integration list resources table with api in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-25 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-029 | Ajax- Integration list bulletins table with api in Front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-26 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-030 | Ajax- Integration post worklog form with api in front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-27 | Kim Il Guk | Min Byong Guk | Assigned
IMS-1-031 | Ajax-Integration list my worklogs table with api in front | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-28 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-041 | Ajax- Integration Approve User API in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-042 | Ajax-Integration api with List Users table in Admin | Make an api for retrieve all registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-043 | Ajax- Integration api with User detail modal in Admin | Make an api to get detail of a selected user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-044 | Ajax- Integration api with List presents table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-045 | Ajax- integration api with List resources table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-046 | Ajax- Integration api with Add resource form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-047 | Ajax- Integration api with Edit resource form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-048 | Ajax- Integration api with Remove resource action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-049 | Ajax- Integration with Approve resource action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-050 | Ajax- Integration with List bulletins table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-051 | Ajax- Integration api with Add builletin form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-052 | Ajax- Integration Edit bulletin form with api in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-053 | Ajax- Integration remove bulletin action with api in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-054 | Ajax- Integration api with Approve bulletin action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-055 | Ajax- List worklog in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-056 | Ajax- Integration api with Approve worklog action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-057 | Ajax- Integration api with List news table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-058 | Ajax- Integration api with Add news form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-059 | Ajax- Integration Edit news in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-060 | Ajax- Integration api with Remove news action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-061 | Ajax- Integration api with List Projects table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-062 | Ajax- Integration api with Add Project form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-063 | Ajax- integration api with Edit project form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-064 | Ajax- Integration api with Remove project action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-065 | Ajax- Integration api with List tasks table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-066 | Ajax- Integration api with Add task form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-067 | Ajax- Integration Edit task form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-068 | Ajax- Integratioon Remove task action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-069 | Ajax- Integration Assign task action/form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-070 | Ajax- Integration api with Compose mail form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-071 | Ajax- Integration api with List mails by type in Admin (Inbox/ draft / trash / sent) | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-072 | Ajax- Integration Trash/Draft mail action in Admin by updating status | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-073 | Ajax- Integration api with List orgnized works table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-074 | Ajax- Integration api with Add daily orgnized work form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-075 | Ajax- Edit daily orgnized work form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-076 | Ajax- Remove daily orgnized work action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-077 | Ajax- Integration api with Update profile form in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-078 | Ajax- Integration api with List advices table in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
IMS-2-079 | Ajax- Integration api with Remove advice action in Admin | Make an api for approving registered user in Admin. Please refer to <APIs> sheet in this excell | 1 | 2016-03-07 | Kim Il Guk | Min Byong Guk | Assigned
Note on B6: Admin 에서 등록된 사용자 승인 등록된 사용자를 승인하는 API를 작성한다. 자료기지에서 active 마당을 1로 설정하는것에 의해 실현할수 있다.
Note on B7: admin에서 사용자자료보기: 자료기지에서 사용자자료를 꺼내여 array형식으로 응답해준다
Note on B8: 사용자자료를 구체적으로 열람한다 다시 말하여 보기에서 모든 자료를 볼수 있게 users와 users_detail을 user_id로서 련결시켜 준다
Note on B9: 출석률 보기 server로부터 출석정보에대한 자료를 받아 admin의 표에 현시할수 있도록 한다
Note on B10: 자원을 보여준다 upload되여 있는 approve된 자료를 보여준다
Note on B11: 자료를 추가해준다
Note on B77: Admin 에서 등록된 사용자 승인 등록된 사용자를 승인하는 API를 작성한다. 자료기지에서 active 마당을 1로 설정하는것에 의해 실현할수 있다.

## APIs-old
Application Programming Interface (Restful API)
Base url: http://localhost/ims/
URL | Method | Request | Response | Description / Related Task
/apis/v1/index.php | GET | { "cmd": "admin-listusers" } | { "code": "200", "aaData": [ array of users ] } | IMS-2-002
/apis/v1/index.php | POST | { "cmd": "admin-approveuser", "userid": 1 } | { "code": "200" } | IMS-2-001
/apis/v1/index.php | GET | { "cmd": "admin-detailuser", "userid":id of user } | { "code": "200", "msg": { "username": "mbk", "gender": "male", … … … "login_stat": "LOGGED_IN" } } | IMS-2-003
/apis/v1/index.php | GET | { "cmd": "admin-listpresents" } | { "code": "200", "aaData": [ array of presented users ] } | IMS-2-004
/apis/v1/index.php | POST | { "cmd": "admin-addresource" } | { "code": "200" } | IMS-2-005
/apis/v1/index.php | POST | { "cmd": "admin-addresources" } | { "code": "200" } | IMS-2-006
/apis/v1/index.php | POST | { "cmd": "admin-editresource", "resource_id": id of the resource } | { "code": "200" } | IMS-2-007
/apis/v1/index.php | POST | { "cmd": "admin-removeresource", "resource_id": id of the resource } | { "code": "200" } | IMS-2-008
/apis/v1/index.php | POST | { "cmd": "admin-approveresource", "resourceid": id of the resource } | { "code": "200" } | IMS-2-009
/apis/v1/index.php | GET | { "cmd": "admin-listbulletins" } | { "code": "200", "aaData":[array of registered bulletins] } | IMS-2-010
/apis/v1/index.php | POST | { "cmd": "admin-addbulletins", "poster_id":id of the poster "bullet_title":title, "bullet_content":content, "bullet_type":type } | { "code": "200" } | IMS-2-011
/apis/v1/index.php | POST | { "cmd": "admin-editbulletins", "bulletins_id":id of bulletins, "poster_id":id of poster, "bullet_title":title, "bullet_content":content, "bullet_type":type } | { "code": "200" } | IMS-2-012
/apis/v1/index.php | POST | { "cmd": "admin-removebulletins", "bulletins_id":id of bulletins } | { "code": "200" } | IMS-2-013
/apis/v1/index.php | POST | { "cmd": "admin-approvebulletins", "bulletins_id":id of bulletins } | { "code": "200" } | IMS-2-014
/apis/v1/index.php | GET | { "cmd": "admin-listworklogs" } | { "code": "200", "aaData":[array of worklogs in mysql] } | IMS-2-015
/apis/v1/index.php |  | { "cmd": "admin-listworklogs" } | { "code": "200" } | IMS-2-016
/apis/v1/index.php |  | { "cmd": "admin-listworklogs" } | { "code": "200" } | IMS-2-017
/apis/v1/index.php |  | { "cmd":"admin-addnews", "subject":"example-subject", "contents":"example-contents", "presenterid":"example-presenterid" } | { "code": "200" } | IMS-2-018
/apis/v1/index.php |  | { "cmd":"admin-editnews", "subject":"example-subject", "contents":"example-contents", "presenterid":"example-presenterid" } | { "code": "200" } | IMS-2-019
/apis/v1/index.php |  | { "cmd":"admin-removenews", "news_id":id of news } | { "code": "200" } | IMS-2-020
/apis/v1/index.php |  | { "cmd":"admin-listprojects" } | { "code": "200" } | IMS-2-021
/apis/v1/index.php |  | { "cmd":"admin-addproject", project_name,customer_id,start_date,end_date,deadline,leader_id,created_date,updated_date,project_status,processed_percent } | { "code": "200" } | IMS-2-022
/apis/v1/index.php |  | { "cmd":"admin-editproject", poster_id,project_name,customer_id,start_date,end_date,deadline,leader_id,created_date,updated_date,project_status,processed_percent } | { "code": "200" } | IMS-2-023
/apis/v1/index.php |  | { "cmd":"admin-removeproject", "project_id":id of remove project } | { "code": "200" } | IMS-2-024
/apis/v1/index.php |  | { "cmd":"admin-addtasks", "taskname": "example-taskname" , "projectid":"example-projectid", "ownerid":"example-projectid", "assigneeid":"example-assigneeid", "priority":"example-priority", "processedpercent":"example-processedpercent" } | { "code": "200" } | IMS-2-025
/apis/v1/index.php |  | { "cmd":"admin-edittasks", "taskname": "example-taskname" , "projectid":"example-projectid", "ownerid":"example-projectid", "assigneeid":"example-assigneeid", "priority":"example-priority", "processedpercent":"example-processedpercent" } | { "code": "200" } | IMS-2-026
/apis/v1/index.php |  | { "cmd": "admin-removetasks", "tasks_id":id of tasks } | { "code": "200" } | IMS-2-027
/apis/v1/index.php |  | { "cmd": "admin-assigntasks", "tasks_id":id of tasks } | { "code": "200" } | IMS-2-028
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-029
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-030
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-031
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-032
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-033
/apis/v1/index.php | GET | { "cmd":"admin-listworkassignments" } | { "code": "200", "aaData":[array of work assignments] } | IMS-2-034
/apis/v1/index.php | POST | { "cmd":"admin-adddailyreport", "reporter_id":id of reporter, "receiver_id":id of receiver, "report_subject":subject of report, "report_content":content of report } | { "code": "200" } | IMS-2-035
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-036
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-037
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-038
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-039
/apis/v1/index.php |  |  | { "code": "200" } | IMS-2-040
/apis/v1/index.php |  |  | { "code": "200" } | IMS-1-001
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }
/apis/v1/index.php |  |  | { "code": "200" }

## Finally Tasks
IMS Project
Goal: |  | Provide a portal any business peoples can use for their office and organization.
Deadline: |  | 2016-04-25
Members: |  | Jang, So, Kim
Task ID | Task Title | Task Description | Deadline | Processor | Assignee | Progress Stat
IMS-001 | 사용자가입 및 등록 | 사용자가입 및 등록을 진행한다. 여기서 등록된 사용자에 대한 가입관리와 가입한 사용자에 대한 SESSION관리를 진행해준다. | 2016-03-15 | Jang Myong Jin | Min Byong Guk | assigned
IMS-002 | 사용자관리 | 등록된 사용자에 대한 approve및 reject기능을 실현하며 가입상태를 관리해준다. | 2016-03-15 | Jang Myong Jin | Min Byong Guk | assigned
IMS-003 | 통신(message)기능 | 통보문을 보내는 기능을 실현한다. 상대방에게 통보문을 보내면 상대방은 일정한 시간간격으로 자기에게 온것이 있는가를 검사하다가 있으면 사용자에게 알려준다. 알려주는 방법은 Toastar Notification을 리용한다. | 2016-03-19 | Kim Il Guk | Min Byong Guk | assigned
IMS-004 | 전자게시판 | 기사 투고 기능 실현 admin쪽에서는 투고된 기사에 대한 approve, reject기능 실현 | 2016-03-16 | So Jong Hyon | Min Byong Guk | assigned
IMS-005 | 자원공유 | 자원의 추가 및 현시, Upload, Download기능, 삭제 및 편집기능 실현(admin) front쪽에서는 Upload와 Download기능실현 | 2016-03-19 | Jang Myong Jin | Min Byong Guk | assigned
IMS-006 | 일보 | 일보 작성 및 1주일전까지의 자료 수정가능 | 2016-03-19 | So Jong Hyon | Min Byong Guk | assigned
IMS-007 | 기본페지 | DB로부터 새소식, 사업포치내용을 얻어서 Front기본페지에 현시. 뿐만아니라 의견함 기능도 가지고 있다. | 2016-03-15 | Kim Il Guk | Min Byong Guk | assigned
IMS-008 | 작업일지 | 하루 작업한 내용을 보고한다. 뿐만아니라 자기에게 할당된 과제를 List로써 볼수 있다. 즉 과제관리자가 과제를 할당해 주면 사용자는 DB로부터 자기에게 할당된 과제만을 볼수있도록 해주어야 한다. Admin쪽에서는 프로젝트관리 및 과제 관리, 할당 등의 기능을 실현 |  |  |  | assigned
Note on B76: Admin 에서 등록된 사용자 승인 등록된 사용자를 승인하는 API를 작성한다. 자료기지에서 active 마당을 1로 설정하는것에 의해 실현할수 있다.